Maintenance Window Design Guide

Planning, Sequencing, and Sizing Maintenance Windows

Architect

| Document ID | MSP-ARC-003 |
| --- | --- |
| Category | Architect |
| Version | 1.0 |
| Audience | Solutions Architect |

# Purpose  —  Test Customer Inc.

This guide helps architects and patching managers design maintenance windows that are appropriately sized, correctly sequenced, and aligned with customer risk tolerance. A poorly designed window is one of the most common causes of patch overruns, rollbacks, and customer incidents.

# 1. Patch Sequencing Principles

When patching multiple device types in the same environment, sequence matters. Incorrect sequencing can cause cascading failures.

| Rule | Explanation |
| --- | --- |
| Network before compute | Patch switches and firewalls before ESXi hosts. If a switch patch causes a connectivity issue, you want to resolve it before VMs are migrated. |
| Storage before hypervisor | Patch SAN arrays before ESXi hosts so that multipath is stable when you put hosts into maintenance mode. |
| Hypervisor before guest OS | Patch ESXi before the VMs running on it. A newly patched ESXi may expose hardware compatibility issues before you're relying on it to host patched workloads. |
| Passive before active | Always patch standby/secondary components first (standby firewall, secondary Exchange DAG member, SQL AG secondary). This preserves the active component until the last step. |
| Test/non-critical first | In environments with dev/UAT and production, patch non-production first. This validates the patch in a lower-risk context. |

# 2. Time Estimation Guidelines

| Device Type | Estimated Time | Includes | Buffer Recommended |
| --- | --- | --- | --- |
| Firewall (HA pair) | 2–3 hrs | Config backup, both unit upgrades, failover, validation | 45 min |
| ESXi host (per host) | 1–2 hrs | vMotion evacuation, patch, reboot, VM validation | 30 min per host |
| SAN (dual controller NDU) | 2–4 hrs | Pre-checks, NDU, multipath validation, backup test | 60 min |
| Switch (per switch) | 45–90 min | Config backup, image staging, reload, validation | 30 min |
| Access Points (per site) | 1–2 hrs | Staging, rolling upgrade, SSID validation | 30 min |
| Exchange Server (CU, per server) | 2–3 hrs | DB move, setup, reboot, health check, mail flow test | 60 min |
| SQL Server (AG, 2 nodes) | 2–4 hrs | Pre-checks, secondary patch, failover, primary patch, validation | 60 min |

TIP: Always add a 25% time buffer to estimated windows. Experienced engineers consistently underestimate patching time, especially for Exchange CUs and multi-host ESXi environments.

# 3. Multi-Device Environment Sequencing Template

| Phase | Device Type | Window Duration | Dependencies Cleared Before Starting |
| --- | --- | --- | --- |
| 1 | Network Switches | 1–2 hrs | None |
| 2 | Firewalls | 2–3 hrs | Switches patched and validated |
| 3 | SAN / Storage | 2–4 hrs | Network stable; all hosts connected |
| 4 | ESXi Hosts (one at a time) | 1–2 hrs each | SAN healthy; cluster at full capacity |
| 5 | Exchange Servers | 2–3 hrs | ESXi and network stable |
| 6 | SQL Servers | 2–4 hrs | ESXi and network stable |
| 7 | Access Points | 1–2 hrs | Switches patched and validated |

# 4. Blackout Period Management

Some customers have periods where no patching is acceptable. Capture these during onboarding and maintain them in your scheduling system.

| Blackout Type | Examples | Handling |
| --- | --- | --- |
| Application freeze | ERP go-live, fiscal year-end, open enrollment | Defer all non-critical patches; apply critical patches with expedited approval |
| Industry blackout | Retail November–December, tax season Jan–April | Pre-plan patches for the periods before and after blackout |
| Customer event | Product launches, conferences, M&A activity | Coordinate with account manager; defer and reschedule |
| Staff availability | Customer IT team on vacation, key contact unavailable | Require on-call designee before proceeding |

# 5. Communication Timeline Template

| When | Communication | Channel | From |
| --- | --- | --- | --- |
| T-5 business days | Patch notification with CR details and maintenance window | Email | Patching Manager or Engineer |
| T-2 business days | Reminder + request for on-call POC confirmation | Email | Engineer |
| T-30 minutes | Window opening notification to NOC and customer POC | Email / Teams | Engineer |
| During window | Status updates if issues arise | Teams / Phone | Engineer |
| Window close | Window closed notification to NOC | Email / Teams | Engineer |
| T+2 business days | Post-patch summary report | Email | Engineer / PM |